## Sheet1
Library Trustees Maintenance Subcommittee Meeting - Minutes
Meeting Date/Time: | WEDNESDAY MAY 17, 2023, at 11:00 AM
Location: S. White Dickinson Library, 202 Chestnut Plain Rd., Whately
Attendees (In Person): Robert Klinger, Larry Ashman, Jim Ross, Fred Orloski
Attendees: (Via Zoom): CynthiaAllen, Cyndi Steiner
Topic: Maintenance Committee Meeting and Building Walk Around, Time: May 17, 2023 11:00 AM Eastern Time (US and Canada)
Minutes:
The Meeting comprised walking around the exterior and interior of the building, starting outside. The spreadsheet below details what we saw and discussed.
Location - Exterior | Item | Description (As Needed) | Condition | Next Steps/Remedy | None, Continue to Observe | Electrical Project | Mason | Keith Bardwell Question
Exterior, West Side (roadside), Main entrance | Front Stairs | Ongoing issue | Concrete spalling and cracking. Some bricks loosing mortar on South end | Library Trustees have approached the Whately CPA about possible CPA funding of repairs. Funding will be voted on at upcoming Town Meeting.
Exterior, West Side (roadside), Main entrance | Front Façade | Main Entry doors | Overall good. Larry commented that the doors where recently repainted. | Careful Powerwash cleaning, painting as needed
Exterior, West Side (roadside), Main entrance | Front Façade | Windows | Overall good. | Careful Powerwash cleaning, painting as needed
Exterior, West Side (roadside), Main entrance | Front Façade | Concrete Lintels | Some cracks are visible, but do not appear to be structural or getting worse. | Continue to observe. Careful Powerwash cleaning, painting as needed
Exterior, West Side (roadside), Main entrance | Front Façade | Brickwork | Overall good. | Careful Powerwash cleaning, painting as needed
Exterior, West Side (roadside), Main entrance | Front Façade | Columns | Some small deteriation at bases, overall look good. | Continue to observe. Careful Powerwash cleaning, painting as needed
Exterior, West Side (roadside), Main entrance | Front door(s) | Front door(s) ADA requirements | They meet requirements, doorbell, automativ opener, width. |  | X
Exterior, West Side (roadside), Children's Room | Roof |  | Looks good. |  | X
Exterior, West Side (roadside), Children's Room | Rain Gutter | Netting, gutter guard type material | Appears to have had a gutter guard installed, netting, that is now become dislodged and needs to be reattached | Maybe Keith can re-attach when he does his next inspection with the lift? |  |  |  | X
Exterior, West Side (roadside), Children's Room | Windows | Two windows First Floor, Children's Room facing West, and one window from entry Foyer facing South. | Look good, relatively new |  | X
Exterior, West Side (roadside), Children's Room | Windows | Basement
Exterior, West Side (roadside), Children's Room | Window Drain | Outside of basement window. | Has some leaves and debris in it. | Maybe Keith can help us with annual cleaning? |  |  |  | X
Exterior, West Side (roadside), Children's Room | Drian Cleanout | Round Green Plastic Cover, with stones around it. This is the cleanout for the basement window drain. | Did not open. No water visible outside of basement window, assuming drain is operating.
Exterior, West Side (roadside), Children's Room | Concrete Lintels and Sills | Lintel - above windows. Sills - below windows | Look good. |  | X
Exterior, West Side (roadside) | ADA ramp | Wooden Posts/columns | Several of the columns exhibit rot at the base and need to be repaired. | As part of front stair work. The ramp may have some work done to it. Possible opportunity to get this done at that time.?
Exterior, South Side, Children's Room | Brick issues | Bricks on corner, just above ground and also higher up wall. | Deterioration on South side of exterior wall. Some bricks are partially missing, some mortar is missing | Get opinion from mason when at Library to do front stairs. |  |  | X
Exterior, South Side, Children's Room | Windows, Lintels and Sills | First Floor and Basement. | Look good. |  | X
Exterior, South Side, Children's Room | Rain Gutter | Netting, gutter guard type material |  | Maybe Keith can check when he does his next inspection with the lift? |  |  |  | X
Exterior, South and East Side & Children's Room | Wooden Trim below roof |  | Showing some signs of paint peeling, corners seperating. | May need to be addressed in future | X
Exterior, East Side, Rotunda | Scuppers | Remove rain from flat roof above Rotunda and pass to downspouts | Keith checks every Fall to make sure fallen leaves do not clog them. | Maintain this cleaning. | X |  |  | X
Exterior, East Side, Rotunda | Brick issues | Mortar and brick damage | Some mortar has fallen out. Some bricks show signs of damage. Note: building was originally painted white then sandblasted to remove the white paint, approx. timeframe - 1970s. | Check with mason on repairing mortar and bricks. Question - is there a sealant or some application we could put on to help protect the brick and mortar? |  |  | X
Exterior, East Side, Rotunda | Windows | First Floor and Basement. | Paint peeling and new glazing | Request has been made to Town for money to repaint Rotunda exterior windows and reglaze. Allocation to be voted on at Town Meeting.
Exterior, East Side, Rotunda | Emergancy Exit Door |  | Replaced and upgraded to meet code as part of Lift project |  | X
Exterior, East Side, Rotunda | Metal Stairs by Exit Door |  | Look good. |  | X
Exterior, East Side, Rotunda | Mini Split Units |  | Currently operating well. | Continue annual maintenance. | X
Exterior, East Side, Rotunda | Roof |  | Looks good. |  | X
Exterior, East Side, Rotunda | Chimneys |  |  | Part of request made to Town for money includes maintenance of both chimneys and capping the unused chimney. Allocation to be voted on at Town Meeting.
Exterior, East Side, Rotunda & North Room | Wooden Trim below roof |  | Showing some signs of paint peeling, corners seperating. | May need to be addressed in future | X
Exterior, NorthSide, North Room | Windows/Lintels and Sills |  | All look good. |  | X
Exterior, NorthSide, North Room | Bricks |  | No obvious issues |  | X
Exterior, NorthSide, North Room | Cabling | Just below roof and enntering building near corner with West side. | All not being used. Can and shouold be removed when possible. | Check with Keith.? |  |  |  | X
Exterior, NorthSide, North Room | Roof |  | Looks good. |  | X
Exterior, NorthSide, North Room | Basement Man-door | Going from storage room to outside. | Needs updating to meet Fire Code. Jim has talked with Greenfield Glass, the existing door can be retrofitted to meet code. | Jim asked Greenfield Glass, who said door could be retrofit, for an estimate.
Exterior, NorthSide, North Room | Basement Man-door |  | Needs to be repainted. | Roger? Maybe as part of cleaning and painting other areas.?
Exterior, NorthSide, North Room | Steel Rails |  | Needs to be repainted. | Needs to be repainted.
Exterior, NorthSide, North Room | Concrete retaining wall |  | Could use pressure washing. |  | X
Exterior, NorthSide | Library Sign |  | Sign looks good. Could use some paint touch up. | Maybe as part of other painting projects.?
Exterior, NorthSide | Bike Rack |  | Looks good.
Outside, yard | Gazebo |  | continue to monitor condition
Location - Interior | Item | Description (As Needed) | Condition | Next Steps/Remedy | None, Continue to Observe | Electrical Project | Mason | Keith Bardwell Question
Interior, General | Lift |  | Operating |  | X
Interior, General | Smoke Detector Upgrades |  | Fire Chief asked that we continue to add Detectors. | Continue to Maintain current Fire Alarm System and upgrade when possible.
Interior/Exterior | Sewer System | Pipe out of building and Septic System | Operating. Septic system is relatively new. Pipe leaving building is primary concern, has been snaked once. |  | X
Interior/Exterior | Mini Splits |  | Operating. Need to have a Heat Loss Study/Energy Audit done again. | Try and find State dollars to redo this. Green Communities Assessment thru Twon is on schedule for next year or two. Currently doing the Elementary School, we should be next. | X
Interior | Electric updates | More outlets - Children's Room, Rotunda, Director's Office, North Stack Room. | Not enough electrical service. | Need to update electrical service. |  | X
Interior, Entryway |  |  | Looks good |  | X
Interior, Children's Room | Windows | Broken Window, South Side | Need to remove and get reglassed. | Need to determine who is doing this.
Interior, Children's Room | Ceiling |  | Some discoloration on West side. | Possible ceiling repaint.?
Interior, North Stack Room | Electric | Plug on North wall | One of the outlets isn't working | Include as part of electrical service update. |  | X
Interior, Basement, Bathrooms |  |  | Look good.
Interior, Basement, Bathrooms | Hot Water |  | Money has been allocated by the Town to add tankless hot water heaters. | Need to make sure adding this type of system, if it goes under the sinks, still meets ADA requirements.
Interior, Basement, Duda Room | Ceiling Lights | Some work, some don't and new bulbs don't help. | Need to have the electrician look into when all other electrical work is done. | Should we get new light fixtures? Concern - do we need to maintain typical light fixtures from time period when the building was built. |  | X
Interior, Basement, Kitchen | Flooring |  | Some rust where the stove used to be. |  | X
Interior, Basement, Kitchen | Outlets | South Wall | Haven't worked since Lift was installed. | Check breaker. Possibly include with Electrical work. |  | X
Interior, Basement, Utility Room | Wall Flaking | South Wall | Mason will patch flaking wall as part of Front Stair project. |  |  |  | X
Interior, Basement, Utility Room | Slop Sink |  | Looking at moving sink in this room to wall next to kitchen.
Interior, Basement, Utility Room | Excess doors |  | Keep in case needed in future. |  | X
Interior, Basement, Utility Room | Door Closer |  | One of excess doors has a closer that needs to be put on the doors going from the foyer in front of the bathrooms into the Duda Room so the doors close in case of a fire. | Needs to be scheduled and done.
Interior, Basement, Boiler Room | Hot water heater, electric |  | Being removed as part of upcoming work.
Interior, Basement, Boiler Room | Cleaning of Boiler | Cleaned 2-3 years ago. | Operated well, when needed this Winter. Jim talked with Bob Keras of Keras Oil | They don't think the boiler gets much work, we can postpone cleaning.
Interior, Basement, Boiler Room | Carbon Monoxide Detector |  | Insurance company asked that one be installed.
Interior, Basement Hall | Smoke Detector | Outside of Bolier Room | Coming up on 10 years old in January 2024. Needs to be replaced.
Interior Basement, Storage Room, North side. | Stair hand rail. | Railing gets too close to wall near top. | Need to have railing cut and a jog installed. | Needs to be scheduled and done. I will check with Blake Gorey when he fabricates a new front, center rail for the front stairs.
Interior Basement, Storage Room, North side. | Cleaning and Organization |  | Need to Get room organized, including Janitorial items all moved into Utility closet.